AI CATALYST HK

AI催化劑香港

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

90-DAY ACTION PLAN V5.0

Pure Media Model | 4-5 hrs/day | Zero Client Work

March 2026 | Version 2.0 | Refined

# Phase Overview

| Phase | Days | Revenue Target | Key Focus |
| --- | --- | --- | --- |
| Foundation | 1-30 | HKD 0 | 10Web site + Notion CRM + 20 blog posts + Newsletter free launch + social setup |
| Content Engine | 31-60 | HKD 0-2,000 | 50 blog posts + Newsletter growth + first digital product + n8n automation |
| Acceleration | 61-90 | HKD 2,000-5,000 | 80 blog posts + 1000+ Newsletter subs + SEO first traffic + first affiliate revenue |

# Phase 1: Foundation (Days 1-30)

## Week 1: Infrastructure (Days 1-7)

Day 1-2: 10Web AI site launch. Register at 10web.io (AI Premium $15/mo). Use AI builder. Install: RankMath, WPML, ThirstyAffiliates, Google Site Kit, WPForms, WP Chat App.

Day 2-3: Notion CRM + MCP setup. Create 6 databases: Subscriber Pipeline, Content Calendar, Affiliate Partners, Newsletter Tracker, Digital Products, Weekly Reviews. Connect Notion MCP via OAuth.

Day 3: Beehiiv newsletter setup. Register beehiiv.com. Brand: name「AI實戰情報」. Embed signup on every 10Web page. Send first free issue immediately.

Day 4-7: Write and publish first 5 blog posts. Set up all social channels: WhatsApp, FB, IG, LinkedIn, Threads. Join affiliate networks: PartnerStack + Impact.com + Reditus (signup URLs in Doc 05 V5).

## Week 2-3: Content Blitz (Days 8-21)

Target: 1 blog post per day, reaching 20 posts by Day 21. Each 2,000-3,000 TC characters. Priority: comparison articles (3-5% conversion) > reviews > listicles. Every post includes: target keyword, 2-3 affiliate links, FAQ schema, Newsletter signup CTA. Daily Newsletter free edition. Social media: n8n auto-generates 15-20 posts/day (Doc 15), you spend 30 min reviewing.

## Week 4: Automation + Review (Days 22-30)

Deploy n8n to VPS. Build core workflows: daily social content generation → Google Drive (Doc 15), new subscriber → Notion, welcome email automation, weekly KPI report. Month 1 review: compile data, identify top-performing content types, set Month 2 targets.

# Phase 2: Content Engine (Days 31-60)

| Week | Focus | Actions | Target |
| --- | --- | --- | --- |
| 5-6 | Content scale | 1 post/day to reach 50 total. FB ads HKD 3,000-5,000/mo for Newsletter growth. | 500-1,000 Newsletter subs |
| 7-8 | Digital product + SEO | Create first digital product 'AI Prompt Engineering Guide' HKD 199-299 (Lemon Squeezy). SEO traffic beginning. | First product sales |

# Phase 3: Acceleration (Days 61-90)

| Week | Focus | Actions | Target |
| --- | --- | --- | --- |
| 9-10 | Systematize | 80 blog posts. Advanced n8n workflows. Prepare Newsletter paid tier (write 2 weeks backlog). | 1,500-2,000 Newsletter subs |
| 11-12 | Launch paid | Newsletter paid tier HKD $68/mo goes live. Send 3 preview issues to free list. Second digital product. Apply to more affiliate programs. | 2,000+ free / 50-100 paid goal |

# Content Production Targets

| Metric | Day 30 | Day 60 | Day 90 |
| --- | --- | --- | --- |
| Blog posts (total) | 20 | 50 | 80 |
| Newsletter free subs | 200-500 | 500-1,000 | 1,500-2,500 |
| Newsletter paid subs | 0 | 0 | 50-100 (launches Day 90) |
| Social media posts (daily) | 15-20 | 20+ | 20+ |
| Digital products | 0 | 1 | 2 |
| Website monthly visitors | 500 | 2,000 | 5,000 |
| Affiliate programs applied | 10+ | 15+ | 20+ |
| Est. monthly revenue (HKD) | 0 | 0-2,000 | 2,000-5,000 |

Cross-reference: Doc 05 V5 (affiliate signup URLs), Doc 09 (10Web setup), Doc 10 (n8n), Doc 14 (Newsletter), Doc 15 (Social Automation)

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

End of 90-Day Action Plan V5.0 | AI Catalyst HK